|  | ## JANUARY | ## FEBRUARY |
| --- | --- | --- |
| ### Steering Committee & ### Full Council | - Council Chair appoints committee chairs and membership - Mentor/Mentee luncheon(s) to welcome new members - Day-long Council Orientation – review annual Timeline of Critical Activities - Set up training for Feb. Steering and Council - Secure locations for all meeting rooms, including off-site Council meetings (July or Aug for Project LEAP) | - 1st Steering Committee and Council meetings - Training in Effective Meeting Management or other skills building training at Steering Committee - Approve the annual Timeline of Critical Council Activities and distribute at all committee meetings and to the community |
| Affected Community | - No meeting | ORIENTATION AT ALL COMMITTEE MEETINGS INCLUDING: - Review goals & timeline - Schedule outreach events (Road 2 Success, health fairs, etc.) in order to recruit Council applicants - Elect a Vice Chair - JOINT MEETING WITH QA TO SELECT CRITERIA |
| Comprehensive HIV Planning | - No meeting unless working on a Needs Assessment or Comp Plan - Start planning for the next Epi Profile | - Review goals and timeline. - Discuss all work products - Elect a Vice Chair |
| Operations | - Committee meets to fine tune January Council Orientation. - Host Mentor/Mentee Luncheon - Host Council Orientation - Set up new external member ½ day orientation | - Review goals & timeline. - Discuss all work products - Sign confidentiality forms - Determine the monthly Council training schedule - General review of policies and procedures, if necessary - Conduct new external member orientation - Elect a Vice Chair |
| Priority & Allocations | - No meeting. | - Committee orientation, including training to read AA reports. - Review allocations based on actual grant award - Approve Principles & Criteria, Priority Setting process and Unspent Funds policy. - If necessary, review revised PC budget from Operations based on actual grant award - JOINT MEETING WITH QA TO SELECT CRITERIA |
| Project LEAP | - Advisory Committee meets to implement student recruitment plan. - Release PR and application forms. | - Recruit student applicants. - Interview applicants. - Secure speakers |
| Quality Assurance | - No meeting - Deadline for submitting Idea Forms | - Joint meeting with P & A, Affected Community & others to establish criteria for selecting the service categories. - Committee orientation, including training to read AA reports. |
| Office of Support | - Submit ad with Council meeting dates (HRSA require.) - Meet with AA’s to review annual Timeline. - Reserve rooms for Public Hearings - Organize HTBMN training. Secure speakers. | - Submit ad with Council meeting dates (HRSA require.) - Staff preps HTBMN workgroup materials. - Invite community to submit input into subcategory allocations. |

|  | MARCH | APRIL |
| --- | --- | --- |
| ### Steering Committee & ### Full Council | - Announce HTBMN Training - APPROVE any documents needed for HTBMN (Needs Assessment? Comp Plan? Epi Profile?) and Criteria for Selecting Service Categories | - After Council: - 3 hour training for How To Best Meet Need (HTBMN) decision-making documents & criteria. - Council Training: HTBMN Process |
| Affected Community | - Consumer Training on HTBMN process - Schedule educational presentations for future meetings - Review Comp Plan task list for this committee | - NO MEETING – ATTEND HTBMN training & workgroup meetings |
| Comprehensive HIV Planning | - Select two presentations for the Public Hearings - Create recommendations from the Needs Assessment and/or Epi Profile for HTBMN - Evaluation Workgroup conducts Comp Plan evaluation - EIIHA Workgroup meets to discuss data needs for next EIIHA Strategy - Review Comp Plan task list for this committee | - NO MEETING - ATTEND HTBMN training & workgroup meetings - Consider a special study if no new Needs Assess or Comp Plan |
| Operations | - Review revised PC budget based on actual grant award and forward to P&A if necessary (due to AA in April) - Review Comp Plan task list for this committee | - NO MEETING - ATTEND HTBMN training & workgroup meetings |
| Priority & Allocations | - May not need to meet | - Attend HTNMN training & workgroup meetings - COMMITTEE MEETS TO: - Review funding requests for unspent monies - Submit Quarterly Report of Committee activities - Review Comp Plan task list for this committee |
| Project LEAP | - Inform student applicants if accepted or not | - Classes begin |
| Quality Assurance | - PR for HTBMN - IMPORTANT: Appoint & train HTBMN workgroup co-chairs - RWGA presents: Chart Reviews, Client Satisfaction and Focus Group results. - Approve checklist for assessing the administrative mechanism - Review Comp Plan task list for this committee | - NO MEETING - ATTEND HTBMN training & workgroup meetings |
| Office of Support | - Create Conflict of Interest List for voting in HTBMN. - Print 2014 – 2015 Blue Book? - Release Subcategory Allocation Review memo – Feb. 14 | - Prepare next year’s Office of Support Budget for the May Operations Committee meeting. Include Blue Book? Needs Assessment? Comp Plan? |

|  | ## MAY | JUNE |
| --- | --- | --- |
| ### Steering Committee & ### Full Council | - Council Training: Priority Setting Process - Approve unspent funds - Provide letter from chair endorsing the revised allocations based on award. (May no longer be needed) | - Approve next year’s service definitions. - Project LEAP students present results of their needs assessments |
| Affected Community | - MAY OR JUNE - Host the Public Hearing on How To Best Meet the Need recommendations. - Submit Quarterly Report of Committee activities | - Host the second Public Hearing on next year’s priorities and allocations. |
| Comprehensive HIV Planning | - Review Council responsibilities in Comp Plan - Develop presentation for the second Public Hearing | - Revise the current Epi Report with complete data from DSHS? - Ask Council to give the committee the authority to approve the new EIIHA strategy. |
| ### Operations | - Operations Committee hosts HTBMN workgroup for Project LEAP & Blue Book. - The committee reviews Council Support Budget (see policy). - Submit Quarterly Report of Committee activities | - Continue to review/revise policies and procedures if necessary. |
| Priority & Allocations | - Approve next year’s priorities - Create timeline for Part B/SS allocations if done separately. Organize a public hearing if done separately. - Submit Quarterly Report of Committee activities | - Hold special meetings to create next year’s allocations. - Approve the allocations at the special meetings with final approval at the regularly scheduled June meeting. - Public Hearing on next year’s recommended priorities & allocations. - Special meeting to review public comment. |
| Project LEAP | - Staff facilitate classes | - Staff facilitate classes |
| Quality Assurance | - Review the subcategory allocation request forms - Approve next year’s HTBMN results - Approve HIV Targeting Chart. - Review subcategory allocation requests. Forward recommendations to P & A by June. - Set date for Sept. joint meeting of P & A, QA and others to determine data needs for all committees next year. Operations may need changes in Oct. for MOU review. - Public Hearing to review next year’s service definitions. - Submit Quarterly Report of Committee activities - Schedule Special Committee meeting to review public comment | - Complete the assessment of the administrative mechanism & send recommended action to Steering. - Review monthly AA reports. - Deadline for submitting idea forms. |
| Office of Support | - Every other year: begin updating Blue Book database |  |

|  | JULY | ## AUGUST |
| --- | --- | --- |
| Steering Committee & Full Council | - Council Training: The Allocations Process - Approve next year’s priorities and allocations. - Approve the assessment of the administrative mechanism and recommended actions. | - Approve anything else needed for the grant application - Approve carryover funds. |
| EIIHA Workgroup | - Approve target populations based approved criteria and new HRSA guidance? |  |
| Affected Community | - Submit Quarterly Report of Committee activities | - Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | - Approve EIIHA Strategy? - Submit Quarterly Report of Committee activities | - Approve EIIHA Strategy? - Continue to work on Comp Plan, Needs Assessment or special studies |
| Operations | - Submit Quarterly Report of Committee activities | - No meeting. |
| Priority & Allocations | - If necessary, fix problems Council has with recommended priorities and allocations for next year. - Allocate carryover funds. - Submit Quarterly Report of Committee activities | - No meeting |
| Project LEAP | - Facilitate classes & host graduation | - Ask Council Chair to appoint all LEAP graduates who apply for Council and committee membership as external committee members. |
| Quality Assurance | - Meet only if needed to: - review Idea forms - submit Quarterly Report of Committee activities | - No meeting. |
| Office of Support | - RESERVE ROOMS FOR NEXT CALENDAR YEAR: ALL COUNCIL & LEAP MEETINGS - Start working on Office of Support portions of the Part A grant application. | - Work on Office of Support portions of the Part A application. |

|  | SEPTEMBER | OCTOBER |
| --- | --- | --- |
| Steering Committee & Full Council | - Council reviews final draft of grant application. Chair submits letter of concurrence according to instructions in HRSA guidance. | - Training: EIIHA Update and Intimate Partner Violence and HIV. - Council Chair selects those who will receive the World AIDS Day Proclamation at Commissioners Court. |
| Affected Community | - Standards of Care Training - Host a Road 2 Success with info re: changes to RW funded services next year? - JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | - Consumer Only SOC Workgroup Meeting - Submit Quarterly Report of Committee activities - Conduct annual committee self-evaluation - Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | - Begin designing the next Needs Assessment or Comp Plan process. OR - Continue to work on Comp Plan, Needs Assessment or special studies | - Continue to work on Comp Plan, Needs Assessment or special studies. - Submit Quarterly Report of Committee activities - Conduct annual committee self-evaluation |
| Operations | - Interview Council applicants - Mail out copy of the MOU for input. - Draft a tool for Council’s self-evaluation in November - Joint Meeting of P & A, QA and others to dialogue about data needs for next year. Operations needs in Oct. | - Interview Council applicants - Ask stakeholders if they wish to revise/revisit the MOU. - Begin to organize December election of officers - Begin to organize the January Council Orientation - Submit Quarterly Report of Committee activities - Conduct annual committee self-evaluation |
| Priority & Allocations | - No meeting - JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | - Allocate unspent funds. - Make plan for carryover funds. Due to HRSA in Dec. - Submit Quarterly Report of Committee activities - Since this is usually the last meeting of the year, review the Committee goals for next year. - Conduct annual committee self-evaluation |
| Quality Assurance | - Deadline for Idea forms. - Submit Quarterly Report of Committee activities - JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | - Participate in the Standards of Care and Performance Measure Work Groups. |
| Office of Support | - Work with Judge’s Office on World AIDS Day Proclamation – Nov. presentation at Commissioners Court - Draft a tool for Council’s self evaluation in November |  |

|  | ## NOVEMBER | DECEMBER |
| --- | --- | --- |
| Full Council | - Approve unspent funds and plan for carryover funds. - Recognize External Committee members. - Conduct annual Council self-evaluation | - Approve recommendations regarding next year’s Standards of Care and Performance Measures. - Acknowledge everyone's hard work. - Hold elections for next year’s RWPC Officers - Chair begins to make committee appointments - Chair begins to organize Mentor Luncheon for mid-January |
| Affected Community | - Prepare for World AIDS Day events - Host a Road 2 Success with info re: changes to RW funded services next year? | - No meeting - Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | - Continue to work on Comp Plan, Needs Assessment or special studies | - No meeting |
| Operations | - Final recommendations to CEO re: Council applicants and next year’s appointees. - Approve Project LEAP service definition | - No meeting - The County Judge announces next year’s Council appointments. - Chair of Planning Council and Chair of Operations conduct Director’s Annual Performance Evaluation. |
| Priority & Allocations | - No meeting | - No meeting |
| Project LEAP | - Prepare evaluation of this year’s Project LEAP - Advisory Committee meets to review Evaluation, make recommendations on the service definition & create a plan for student recruitment. - Create calendar for next year’s Project LEAP | - Set up December or January Advisory Committee meeting to start recruiting student applicants. |
| Quality Assurance | - Approve recommendations to next year’s Standards of Care and Performance Measures. - Review Quarterly Reports from AAs - Submit Quarterly Report of Committee activities - Conduct annual committee self-evaluation | - No meeting |
| Office of Support | - Director works with CEO on new Council appointments that start January 1st. | - HRSA meeting in Washington DC - Manager conducts annual performance evaluation of all support staff. - Manager creates next year’s Council Timeline of Critical Activities. - Remind Council members to turn in receipts before Feb. 15th and March 30th. |

NEXT NEEDS ASSESSMENT – Collect data in 2019